DSTERMINAL PROJECT

Technical Progress and Grant Utilization Report

Project Title: DSTerminal (Defensive Security Terminal)

Report Period: June – July 2026

Submitted To: The Director General, NCST

Submitted By: Spark Wilson Spink - Project Lead

Contact: (+265) 993 076 724 / 886 283 247

# 1. EXECUTIVE SUMMARY

This report provides an update on the DSTerminal Project's progress following grant support from NCST.

DSTerminal v3.1.113 has been successfully developed, packaged, and branded. The software is now at Pre-Release stage with 85% core development completion. The project has utilized MWK 3,135,000 of the total MWK 5,000,000 grant, leaving a balance of MWK 1,865,000.

Current Status:

Software packaging and branding complete

Production-ready installers available (Windows and Linux)

All 9 core security modules operational

Internal testing: 90% complete

External pilot testing: Not yet started

Commercialization: Not yet started

# 2. PROJECT STATUS SUMMARY

| Indicator | Status | Progress |
| --- | --- | --- |
| Grant Received | Yes – 100% | ✓ |
| Software Development | 85% Complete | ↑ |
| Internal Testing | 90% Complete | ↑ |
| Software Packaging | Complete | ✓ |
| Equipment Procurement | 85% Complete | ↑ |
| External Pilot Testing | 0% | ✗ |
| Commercialization | 0% | ✗ |

# 3. TECHNICAL ACHIEVEMENTS

## 3.1 Software Modules Completed

| Module | Status |
| --- | --- |
| VirusTotal Scanner | ✓ |
| Network Reconnaissance | ✓ |
| Web Security Analyzer | ✓ |
| Encryption Engine | ✓ |
| SQLMap Integration | ✓ |
| Wi-Fi Auditor | ✓ |
| System Hardening | ✓ |
| Digital Forensics | ✓ |
| SSL/TLS Scanner | ✓ |

## 3.2 Packaging and Branding Completed

Windows Installer (304 MB) with all dependencies

Portable ZIP version (255 MB)

Linux server compatibility

User documentation and command reference

Professional branding with NCST acknowledgment

Both Licensed and Non-Licensed DSTerminal installers have been packaged and branded, ready for pilot testing deployment.

The DSTerminal installer is dependency-aware with all required libraries bundled. It does not require internet access during installation and does not need external dependencies to be installed or configured by users.

# 4. EQUIPMENT PROCUREMENT

| Item | Cost (MWK) |
| --- | --- |
| Desktop Workstation | 1,250,000 |
| HP Laptop (Testing) | 750,000 |
| Airtel ODU Router | 425,000 |
| External HDD (1TB) | 70,000 |
| Packaging and Branding | 320,000 |
| API Integration and Patching | 300,000 |
| Transportation | 20,000 |
| Total Spent | 3,135,000 |
| Remaining Balance | 1,865,000 |

# 5. CHALLENGES AND FUNDING SHORTFALL

## 5.1 Key Challenges

| Challenge | Impact |
| --- | --- |
| Rising Equipment Costs | Reduced purchasing power, delayed some planned procurements |
| High External Testing Costs | Pilot testing requires infrastructure, personnel, and logistics |
| Continuous Development Needs | Bug fixes, security updates, and feature enhancements require ongoing resources |

## 5.2 Critical Funding Shortfall

The remaining MWK 1,865,000 is insufficient to cover all planned activities and critical requirements needed to complete the project successfully:

| Activity | Estimated Cost (MWK) |
| --- | --- |
| External Beta Testing Program | 800,000 |
| Pilot Deployment at Institutions | 600,000 |
| Security Audits and Penetration Testing | 700,000 |
| Training Content and Workshops | 500,000 |
| Legal and IP Registration | 400,000 |
| Continuous Development Support | 500,000 |
| Marketing and Commercialization | 500,000 |
| Monitoring and Evaluation | 200,000 |
| Contingency | 300,000 |
| Total Required | 4,500,000 |
| Available Balance | 1,865,000 |
| Shortfall | 2,635,000 |

# 6. FUTURE ACTIVITIES

## 6.1 Activities Requiring Additional Funding

The following activities cannot be completed with the remaining funds and require additional financial support:

| Activity | Cost (MWK) | Justification |
| --- | --- | --- |
| External Beta Testing | 800,000 | Essential to validate software stability and gather user feedback before public release. Includes tester incentives, platform costs, and logistics. |
| Pilot Deployment | 600,000 | Deploy software at partner institutions to demonstrate real-world application and provide case studies necessary for commercialization. |
| Security Audits and Penetration Testing | 700,000 | Critical to validate the security claims of the software, identify vulnerabilities, and build trust with potential users. |
| Legal and IP Registration | 400,000 | Necessary to protect intellectual property rights, enabling future commercialization and sustainability. |
| Marketing and Commercialization | 500,000 | Essential for market entry, business model development, and achieving project sustainability beyond the grant period. |
| Training Content and Workshops | 500,000 | Enables end-user adoption, builds community of practice, and supports technology transfer. |
| Monitoring and Evaluation | 200,000 | Required to measure project impact, track outcomes, and provide accountability to NCST. |
| Total Additional Funding Requested | 4,500,000 |  |

## 6.2 Planned Activities with Remaining Funds (MWK 1,865,000)

| Activity | Timeline | Cost (MWK) |
| --- | --- | --- |
| External Beta Testing (Partial) | Aug–Sep 2026 | 500,000 |
| Pilot Deployment (1 Institution) | Sep 2026 | 400,000 |
| Basic Training Content | Aug 2026 | 250,000 |
| Internal Security Reviews | Ongoing | 200,000 |
| Bug Fixes and Maintenance | Ongoing | 300,000 |
| Monitoring and Evaluation (Partial) | Oct 2026 | 100,000 |
| Contingency |  | 115,000 |
| Total |  | 1,865,000 |

## 6.3 Activities That Will Be Deferred Without Additional Funding

Comprehensive external security audit (MWK 700,000)

Full-scale pilot deployment (MWK 600,000)

IP registration (MWK 400,000)

Marketing and commercialization activities (MWK 500,000)

Expanded training and workshops (MWK 500,000)

# 7. CONCLUSION AND RECOMMENDATIONS

## 7.1 Conclusion

DSTerminal has achieved significant technical milestones with NCST support. The software is now ready for external validation, but MWK 4,500,000 is needed to complete all remaining activities successfully.

The available balance of MWK 1,865,000 is insufficient to cover external testing, pilot deployment, security validation, legal protection, and commercialization—all of which are essential for the project's success and sustainability.

## 7.2 Recommendations for NCST

1. Consider additional funding of MWK 4,500,000 to cover all critical remaining activities:

- External beta testing and pilot deployment

- Comprehensive security audits

- IP registration and legal protection

- Marketing, commercialization, and sustainability

- Training content and workshops

- Continuous development support

- Monitoring and evaluation

2. Facilitate connections – Introduce the project to potential institutional partners for pilot deployment.

3. Provide commercialization guidance – Support with market entry and business model development.

# 8. ACKNOWLEDGEMENT

I sincerely thank NCST for the continued support. The grant has been instrumental in advancing DSTerminal from concept to a functional, packaged software product ready for external validation.

Prepared By:

Spark Wilson Spink

Project Lead, DSTerminal

Date: July 24, 2026

# 9. SUMMARY OF FUNDING REQUIREMENTS

| Item | Amount (MWK) |
| --- | --- |
| Total Grant Received | 5,000,000 |
| Total Spent to Date | 3,135,000 |
| Remaining Balance | 1,865,000 |
| Total Required to Complete Project | 4,500,000 |
| Additional Funding Requested | 4,500,000 |